## Launch Checklist
CLARITECT - REMAINING LAUNCH CHECKLIST
42 remaining items across 3 launch buckets. Items already assessed as done are removed. Email delivery and SSL/TLS everywhere were intentionally removed from this workbook.
Total remaining: 42 | Partial: 10 | Open: 32 | Categories: Main product / Marketing pages / Non-UI and backend related
Done | Category | Status | Item | Details | Notes
☐ | Main product (post-login pages) | Partial | Report quality at consultant level | Tighten narrative quality, chart polish, findings, and recommendation quality so the final output feels board-ready.
☐ |  | Partial | Error handling polish | Customer-facing failures should feel calm and actionable across chat, reports, scheduling, and connection setup.
☐ |  | Partial | Progress indicators | All long-running actions should show clear step-based progress instead of feeling stalled.
☐ |  | Partial | Mobile-responsive reports | Report views need a final quality pass for mobile readability and hierarchy.
☐ | Marketing pages (pre-login pages) | Partial | One-click demo flow | The public site should move a prospect from curiosity to first live answer with minimal friction.
☐ |  | Partial | Pilot booking flow | Replace light CTA handling with a proper booking path for live pilots.
☐ |  | Partial | ROI calculation ready | Have a tighter and more explicit launch-ready ROI comparison that sales can use live.
☐ |  | Open | 3 example reports on website | Publish example finance, operations, and business-case outputs so visitors can see what Claritect produces.
☐ |  | Open | 30-second product video | Short screen-led loop showing question to report in a few beats.
☐ |  | Open | 2-3 minute demo video | A fuller walkthrough for buyers who want the complete product story before a call.
☐ |  | Open | Blog with 2-3 SEO articles | Seed early search visibility with launch-adjacent thought pieces and use cases.
☐ |  | Open | Favicon, OG tags, meta descriptions | Add the final metadata and sharing polish so the public pages look credible when shared.
☐ | Non-UI and backend related | Partial | SOC 2 readiness | Not certification yet. Document practices, access logging, encryption, and operational controls.
☐ |  | Partial | Usage metering per tenant | The foundations exist, but launch-grade tenant metering for limits and billing should be tightened.
☐ |  | Partial | Usage dashboard for yourself | You need an internal operator view of tenant usage, cost, and report volume.
☐ |  | Open | Data handling policy | Document what data is stored, for how long, and how generated evidence and runs are handled.
☐ |  | Open | Terms of Service | Customer-facing legal terms covering liability, acceptable use, and service boundaries.
☐ |  | Open | Privacy Policy | A publishable privacy statement aligned with how the application handles customer and user data.
☐ |  | Open | Security one-pager PDF | A compact trust document answering the first security-review questions without requiring a meeting.
☐ |  | Open | Production deployment | Move from local/dev readiness to a real deployed environment with repeatable rollout steps.
☐ |  | Open | Custom domain | Serve the production app on the real Claritect domain, not a temporary or platform hostname.
☐ |  | Open | Automated daily backups | Back up the metadata layer and validate restore confidence before launch.
☐ |  | Open | Uptime monitoring | Track application availability externally so outages are caught before customers report them.
☐ |  | Open | Error alerting | Add operational alerting for API, worker, scheduler, and report-generation failures.
☐ |  | Open | Rate limiting per tenant | Protect the shared LLM/runtime budget from abuse or accidental overconsumption.
☐ |  | Open | Environment separation | Keep production and staging cleanly separated so testing never touches live customer workflows.
☐ |  | Open | Pilot demo script | A rehearsed sequence for live pilots so every session feels deliberate and repeatable.
☐ |  | Open | 5 killer demo questions prepared | A short list of compelling recurring business questions ready for finance, operations, product, and leadership.
☐ |  | Open | Backup demo recording | A fallback walkthrough in case a live pilot is disrupted by data, networking, or model latency issues.
☐ |  | Open | Follow-up email template | A reusable post-pilot email covering what was shown, next steps, pricing, and access links.
☐ |  | Open | Proposal template | A simple commercial proposal that can be turned around quickly after a successful pilot.
☐ |  | Open | CRM | Even a lightweight system is enough, but leads and follow-up dates need a consistent home.
☐ |  | Open | Business entity registered | Formal business structure in place before taking recurring commercial payments.
☐ |  | Open | Business bank account | Separate business finances from personal operations before live billing starts.
☐ |  | Open | Stripe account verified | Complete billing setup and test live payment behavior end to end.
☐ |  | Open | Professional invoices | Ensure invoices have the expected branding, business details, and customer-facing polish.
☐ |  | Open | Cancellation flow | Define and implement the customer offboarding path clearly before charging real accounts.
☐ |  | Open | Refund policy | Have a plain-language refund stance ready before launch conversations start.
☐ |  | Open | Contract template | A lightweight agreement for early customers so the sales cycle does not stall on paperwork.
☐ |  | Open | Customer onboarding email sequence | A simple post-signup sequence to get new customers from connection to first recurring report.
☐ |  | Open | Weekly check-in with first 5 customers | A founder-led feedback loop for the first set of paying or pilot customers.
☐ |  | Open | Collect testimonials | Capture short quotes once early customers have successful live outcomes.
Suggested use: close Main product first, then Marketing pages, then the Non-UI and backend related launch layer.